## Info
8D-Report We want to give you a quick and easy introduction to an 8D report and have created this template for you. You can process complaints even more easily and effectively in our Complaint Management module. You can find more information on this at: www.qmbase.com For more information on the 8D report and other QM methods, see:
https://www.qmbase.com/en/8d-report/

## 8D-Report
Template 8D-Report
D1: Assembling a team
Problemsolvingteam | Distributor for reports
P. Mayer, L. Distelkamp, M. Vieten | P. Müller, S. Schneider
D2: Problem description
Customer XYZ received two defective pipes of type 12345 in delivery 112/16 dated 08.16.2020
D3: Define immediate measures
Replacement delivery of two new mechanical seals type 12345 (responsible: L. Distelkamp, deadline: 08.10.2020)
Introduce 100% testing in the current production of mechanical seals of type 12345. (Responsible: M. Vieten, deadline: 08.20.2020)
100% check all mechanical seals of type 12345 existing in the house and rework if necessary. (Responsible: M. Vieten, deadline: 08.21.2020)
D4: Determine cause(s) of error
A new supplier (XYZ) was used for BOM item 14. This supplier delivered faulty goods.
D5: Planning of remedial measures
100% inspection of deliveries from supplier XYZ for BOM Pos. 14 (responsible: M. Vieten, deadline: 08.25.2020)
D6: Introduction of the shutdown measures
Adjustment of test instructions in goods receipt for supplier XYZ for BOM Item 14 Mechanical seal type 12345 (Responsible: P. Mayer, deadline: 08.25.2020)
Train employees in goods receipt. (Responsible: P. Mayer, deadline: 08.26.2020)
Cancel 100% inspection in the current production of mechanical seals of type 12345. (Responsible: M. Vieten, deadline: 08.27.2020)
D7: Prevent error repetition
Adaptation of the testing processes for new suppliers. (Responsible: P. Mayer, deadline: 08.30.2020)
Display inspection instructions more prominently in the goods receipt. (Responsible: P. Mayer, deadline: 05.09.2020)
The problem is included in the FMEA checklist for mechanical seals. (Responsible: M. Vieten, deadline: 09.19.2020)
D8: Recognition of the team performance
All measures defined in the report were successfully implemented. The team is thanked for its cooperation. (Responsible: M. Vieten, completion date: 10.09.2020)